## Actual
|  | 15th Feb | 22nd Feb | 1st Mar | 8th Mar | 15th Mar | 22nd Mar | 29th Mar | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | Easter | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14
Report
Create an account
Load template
Read guidelines
Deliverables
Create GIT Account
Share with lecturer
Commit regularly
Record prototype
Upload VIVA
Submit report
Research Methodology
Hypothesis
Research Questions
Research Methods
Research Pipeline
Finalise section in report
Literature Review
Review datasets
Review algorithms
Review evaluation metrics
Finalise section in report
Prototype
Find Base Game
Create player performance dataset
Tweek Game to Record player performance
Create levels that scale based on player performance | bar: WK7 to WK8
Get feedback from players
Discussion of Results
Write prototype evaluation
Write dataset evaluation
Write hypothesis testing
Write project evaluation
Finalise section in report
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations
Finalise Introduction
Finalise Abstract