## Actual
|  | 15th Feb | 22nd Feb | 1st Mar | 8th Mar | 15th Mar | 22nd Mar | 29th Mar | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | Easter | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14
Report
Create an account
Load template
Read guidelines | bar: WK7 to WK12
Deliverables
Create GIT Account
Share with lecturer
Commit regularly | bar: WK7 to WK12
Record prototype
Upload VIVA
Submit report
Research Methodology
Hypothesis
Research Questions
Research Methods | bar: WK11
Research Pipeline | bar: WK11
Finalise section in report | bar: WK11 to WK12
Literature Review
Review datasets
Review evaluation metrics
Finalise section in report
Prototype
Find Base Game
Create player performance dataset
Tweek Game to Record player performance
Create levels that scale based on player performance | bar: WK7
Get feedback from players | bar: WK8
Discussion of Results
Write prototype evaluation | bar: WK9
Write dataset evaluation | bar: WK9
Write hypothesis testing | bar: WK10
Write project evaluation | bar: WK10
Finalise section in report | bar: WK10 to WK12
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations | bar: WK11 to WK12
Finalise Introduction | bar: WK11 to WK12
Finalise Abstract | bar: WK11 to WK12